## Sheet1
LOGICAL FRAMEWORK MATRIX: Disaster Preparedness and Prevention Initiative (DPPI) Project - Joint Emergency Response Unitsin in case of floods in Sout Eastern Europe | [17 empty] | Appendix C
Wider | Enhancing the co-operation between countries in the SEE in case of natural and man made disaster |  |  |  |  | Reduction of consequences and damages caused by natural and man made disaster in the countries of South Easter Europe |  |  |  |  | Establishing regional mechanism for co-operation and co-ordination preparedness and prevention activities in the region of SEE
Objectives
Specific Objectives of the Technical Assistance that have Objectively Verifiable Indicators
Overall | Capabilities of National Disaster Management Authorities in the region of SEE enhanced |  |  | I. | Establishing Joint Emergency Response Units Project Co-ordination Team
Objectives |  |  |  | II. | Establishing Joint Emergency Response Units
|  |  |  | III. | Procurement of Equipment
|  |  |  | IV. | Developing Border Crossing Procedures/Protocols
|  |  |  | V. | Organize Field Exercise of the Joint Emergency Response Units
|  |  |  | VI. | Co-ordination and Co-operation with relevant National and International Authorities, Institutions and Organizations
End State | Regional and inter state mechanism for joint coordination and management in case of floods enhanced and DPPI strengthen at Local, National and Regional level |  |  | VII. | Donors and National Authorities timely and adequately informed
Objective
Output | I |  | II |  |  |  | III |  | IV |  |  | V |  | VI |  | VII
| Establishing team for joint co-ordination activities - the Project Joint Emergency Response Units |  | Establishing Joint Emergency Response Units |  |  |  | Procurement of Equipment |  | Developing Border Crossing Procedures/Protocols |  |  | Organized Field Exercise of the Joint Emergency Response Units |  | Co-ordination with relevant National and International Authorities, Institutions and Organizations |  | Donors and National Authorities timely and adequtely informed
Specific Objectives
and
| The Joint Emergency Response Units Project Co-ordination Team established |  | The Joint emergency Response Units established |  |  |  | Equipment procured, distributed among countries and used by the JERU |  | Border Crossing Procedures/Protocols developed and agreed |  |  | JERU through the Field Exercise confirmed their preparedness to response in case of floods in the region |  | Co-ordinations with relevant National and International authorities, Institutions and Organizations established, maintained and enhanced |  | Current and accurate reporting mechanisms developed and Donors and National Authorities adequtely informed on all aspects of the project
Results
Outline of Approach Proposed for Project Implementation
Approach | a. | Conduct regular meetings between JERU PCT | a. | Networking with Training Providers |  |  | a. | Preparing List of the Equipment for JERU | a. | Preparing drafts of the Protocols |  | a. | Inquiry for the Field Exercise location | a. | To Participate on meetings regarding Disaster Management organized by National Authorities | a. | JERU PCT will report to the National
and |  |  | b. | List of Team Leaders for Joint Emergency Response Course |  |  |  |  | b. | Establish close co-operation with International and National experts in the field of Border Crossing | [6 empty] | Governments on regular basis
Activities | b. | Contacts between JERU PCT and IO |  |  |  |  | b. | Contact with potential Equipment Procurer |  |  |  | b. | Survey of the target locations with national experts |  |  | b. | JERU PCT will report to the Donors on
|  |  | c. | List of candidates for Joint Emergency Response Units | [9 empty] | b. | To attend Conferencesand meetings organize by International Institutions and Organisations |  | regular basis
| c. | Contacts between regional CP/NDMA |  |  |  |  | c. | Preparing documentation for International Tendered | c. | Obtaining approvals from respective National Governments |  | c. | Preparing roster for the Field Exercise
[14 empty] | c. | Organize International Conference on flood management in SEE region
| d. | Contacts between JERU PCT and relevant National and International Authorities
| e. | Electronic exchanging information
Workshop Manager, Appt of Plant Ops
Officer and EDD Ops Officer
[7 empty] | j. | Monitor UNHCR Demining Units
Asset Integration
Indicators | a. | Each parties involved in Project will | a. | No. of days spent on Training Course |  |  | a. | International procurement and tenders | a. | Drafts of the Protocols |  | a. | No. of JERU Teams participate | a. | Co-ordination between parties involved in the project | a. | Minutes of Meeting and Progress Reports to the National Governments and Donors
of |  | nominate minimum one person | [6 empty] | b. | National and International Experts involved in the JERU CT work |  | b. | No. of Floods Exercise
Achievements |  | as member of the JERU PCT | b. | No. of participants successfully passed training course |  |  | b. | Ensure that equipment is used for the purposes stated in the project | [5 empty] | b. | Co-ordination and Liaising with relevant authorities, institutions and organization at the local level | b. | Inception and Interim Reports to the relevant National Governements and Donors
| b. | 11 National representatives in the JERU PCT | [6 empty] | c. | Approvals for Boreder Crossing Protocols to be signed |  | c. | No of Combines Emergency Response Tasks
|  |  | c. | No of Joint Emergency Response Units formed | [7 empty] | d. | No. of International Org. particiapte | c. | Co-ordination with relevant International Institutions and organizations | d. | Final Report to the National Governments and Donors
| c. | 2 DPPI representatives in the JERU PCT
|  |  | d. | Structures of Joint Emergency | [11 empty] | c. | All this reporting to the Donors will be
| d. | International Experts in the JERU PCT |  | Response Units | [12 empty] | performed through the DPPI SEE Secretariat